## Slide 1
Part 7: Decision Points & Next Steps

## Slide 2
Slide Five Key Decisions for CISAC
Strategic Decisions Required (November 2025)
DECISION 1: Approve Knowledge Transfer Pilot Test?
┌────────────────────────────────────────────────────────┐
│ Investment: €10-20K │
│ Timeline: December 2025 - February 2026 (2 months) │
│ Risk: Very Low (non-critical feature) │
│ │
│ OUR RECOMMENDATION: ✅ YES (High Priority) │
│ │
│ Rationale: Single most important data point for vendor │
│ independence strategy. €10-20K investment │
│ de-risks €300-600K decision. │
│ │
│ Action Required: │
│ • Define pilot feature scope │
│ • Identify independent vendors to approach │
│ • Allocate budget approval │
│ • Timeline: Start December 2025 │
•───────────────────────────────────────────────────────┘
DECISION 2: Initiate Contract Renegotiation?
┌────────────────────────────────────────────────────────┐
│ Investment: Minimal (legal/negotiation time) │
│ Timeline: December 2025 - March 2026 (parallel to pilot)│
│ Risk: Low (worst case: status quo continues) │
│ │
│ OUR RECOMMENDATION: ✅ YES (High Priority) │
│ │
│ Rationale: Use audit findings as leverage. Better │
│ terms achievable whether CISAC stays or │
│ switches vendors. │
│ │
│ Priority Terms: │
│ • CRITICAL: Git history, IaC templates, cost tooling │
│ • HIGH: Performance SLAs, enhanced DoD, metrics sharing│
│ • MEDIUM: Knowledge transfer docs, ADR practice │
│ │
│ Action Required: │
│ • Authorize Yann to lead negotiation │
│ • Define priority vs negotiable terms │
│ • Timeline: Initiate December 2025 │
•───────────────────────────────────────────────────────┘
DECISION 3: Approve Hyperscale Proposal (PSA 5499)?
┌────────────────────────────────────────────────────────┐
│ Investment: €40K migration + €1,800/month savings │
│ Timeline: Migration ~2-3 months after approval │
│ Risk: Medium (reserved instance = 1-year commitment) │
│ │
│ OUR RECOMMENDATION: ⚠️ HOLD Pending Validation │
│ │
│ Rationale: Bottleneck not validated. Query optimization│
│ may achieve similar results at lower cost. │
│ Secondary priority vs governance issues. │
│ │
│ Actions BEFORE Approval: │
│ • Meet with Moïse (production performance data) │
│ • Validate SQL Server bottleneck │
│ • Explore query optimization alternative (€5-10K) │
│ • Decision by March 2026 with data │
•───────────────────────────────────────────────────────┘
DECISION 4: Research Alternative Matching Engine Vendors?
┌────────────────────────────────────────────────────────┐
│ Investment: €5-10K (market research, vendor proposals) │
│ Timeline: December 2025 - February 2026 (parallel) │
│ Risk: Very Low (research only, no commitment) │
│ │
│ OUR RECOMMENDATION: ✅ YES (Medium Priority) │
│ │
│ Rationale: Strengthens negotiating position even if │
│ CISAC never switches. Informs long-term │
│ strategy. Low cost for high strategic value. │
│ │
│ Scope: │
│ • Identify alternative matching engine vendors │
│ • Request proposals and demos │
│ • Assess functionality comparison │
│ • Evaluate API compatibility and integration effort │
│ │
│ Action Required: │
│ • Define matching engine requirements spec │
│ • Research music rights technology vendors │
│ • Timeline: Start January 2026 │
•───────────────────────────────────────────────────────┘
DECISION 5: Vendor Relationship Strategy Going Forward?
┌────────────────────────────────────────────────────────┐
│ Timeline: Decision by March 2026 (after Phase 1 results)│
│ Risk: Depends on path chosen │
│ │
│ OUR RECOMMENDATION: ⏸️ DEFER Until Phase 1 Complete │
│ │
│ Rationale: Don't decide today. Wait for: │
│ • Pilot test results (Feb 2026) │
│ • Market research results (Feb 2026) │
│ • Negotiation outcomes (ongoing) │
│ │
│ Possible Paths (decide with data): │
│ │
│ Path A: Vendor Transition │
│ IF: Pilot successful + Alternatives exist │
│ → 12-24 months, €300-600K, high risk, full independence│
│ │
│ Path B: Improved Relationship │
│ IF: Pilot fails OR no alternatives │
│ → Immediate, minimal cost, medium risk, better terms│
│ │
│ Path C: Partial Independence │
│ IF: Mixed results │
│ → Split model: new vendor (app) + Spanish Point (ME)│
│ │
│ Decision Timeline: March 2026 with Phase 1 data │
•───────────────────────────────────────────────────────┘
graph TD
A[Five Key Decisions] --> B[1. Pilot Test?]
A --> C[2. Contract Negotiation?]
A --> D[3. Hyperscale Approval?]
A --> E[4. Market Research?]
A --> F[5. Vendor Strategy?]
B -->|YES ✅| G[Dec 2025 - Feb 2026<br/>€10-20K]
C -->|YES ✅| H[Dec 2025 - Mar 2026<br/>Parallel to pilot]
D -->|HOLD ⚠️| I[Validate first<br/>Decision Mar 2026]
E -->|YES ✅| J[Jan 2026 - Feb 2026<br/>€5-10K]
F -->|DEFER ⏸️| K[Decide Mar 2026<br/>After Phase 1 data]
style B fill:#90EE90
style C fill:#90EE90
style D fill:#FFD700
style E fill:#90EE90
style F fill:#87CEEB
Notes: Let's crystallize the decisions CISAC leadership must make.
**Decision 1: Approve Knowledge Transfer Pilot Test?**
**Our recommendation: ✅ YES (High Priority)**
This is the single most important investment. €10-20K to validate the €300-600K vendor switch assumption. Start December 2025.
Actions required:
- Define pilot feature (work with Yann/Moïse)
- Identify independent vendors to approach (French/European .NET shops)
- Allocate budget approval
**Decision 2: Initiate Contract Renegotiation?**
**Our recommendation: ✅ YES (High Priority)**
Use audit findings as leverage. Better terms benefit CISAC whether you stay or switch. Start December 2025, run parallel to pilot test.
Priority terms:
- CRITICAL: Git history access, IaC templates, cost correlation tooling
- HIGH: Performance SLAs, enhanced DoD, proactive metrics
- MEDIUM: Knowledge transfer docs, ADR practice
Action required: Authorize Yann to lead negotiation.
**Decision 3: Approve Hyperscale Proposal?**
**Our recommendation: ⚠️ HOLD Pending Validation**
€40K investment + reserved instance commitment requires performance justification we don't have. Validate SQL bottleneck first. Explore query optimization alternative (€5-10K).
Decision timeline: March 2026 after validation.
This is SECONDARY priority - governance and vendor strategy are more important.
**Decision 4: Research Alternative Matching Engine Vendors?**
**Our recommendation: ✅ YES (Medium Priority)**
€5-10K market research. Low cost, high strategic value. Strengthens negotiating position even if CISAC never switches.
Start January 2026.
**Decision 5: Vendor Relationship Strategy Going Forward?**
**Our recommendation: ⏸️ DEFER Until Phase 1 Complete**
Don't decide today. Wait for:
- Pilot test results (February 2026)
- Market research results (February 2026)
- Negotiation outcomes (ongoing through March 2026)
Then decide between Path A (vendor transition), Path B (improved relationship), or Path C (partial independence) with actual data.
Decision timeline: March 2026.
**Summary of Recommendations:**
- ✅ **YES:** Pilot test, contract negotiation, market research
- ⚠️ **HOLD:** Hyperscale proposal (validate first)
- ⏸️ **DEFER:** Final vendor strategy (decide with data in March 2026)
**Discussion Prompt:** Are there other decisions we haven't addressed that CISAC leadership needs to make?

## Slide 3
Slide Immediate Next Steps (December 2025 - March 2026)
Phase 1 Implementation Timeline (Dec 2025 - Mar 2026)
DECEMBER 2025 - Launch Phase
Week 1-2:
☐ Pilot Test Setup
  • Define pilot feature scope (CISAC + Audit Team)
  • Identify 3-5 independent vendors (.NET expertise)
  • Prepare RFP materials (code, docs, spec)
  • Send RFP, collect proposals
☐ Contract Renegotiation Preparation
  • Document audit findings (this presentation + detailed report)
  • Prioritize contract terms (critical vs nice-to-have)
  • Legal review of current contract
  • Schedule negotiation kickoff meeting with Spanish Point
☐ Technical Quick Wins
  • URGENT: Escalate pipeline test runner fix
  • Request Databricks upgrade roadmap (due Dec 31)
  • Schedule January cost review meeting
Week 3-4:
☐ Pilot Test Launch
  • Select pilot vendor (evaluation of proposals)
  • Contract signed, NDA in place
  • Kickoff meeting, materials delivered
  • Development begins
☐ Contract Negotiation Kickoff
  • Present audit findings to Spanish Point
  • Request git history access (immediate priority)
  • Request IaC templates inclusion
  • Discuss cost correlation tooling options
JANUARY 2026 - Execution Phase
Week 1-2:
☐ Pilot Test Monitoring
  • Weekly check-ins with pilot vendor
  • Track questions, challenges, progress
  • Document Spanish Point cooperation level
☐ Matching Engine Market Research
  • Identify alternative vendors (music rights tech)
  • Request proposals and technical documentation
  • Schedule vendor demos/presentations
☐ Performance Validation
  • Meet with Moïse (production metrics, user complaints)
  • Review Application Insights data (SQL performance)
  • Document actual vs. claimed performance
Week 3-4:
☐ Monthly Cost Review (First Meeting)
  • CISAC + Spanish Point + Finance
  • Review Dec 2025 spending
  • Manually correlate with usage (until tooling exists)
  • Identify anomalies, action items
☐ Contract Negotiation Progress
  • Git history access resolved? (should be immediate)
  • IaC templates negotiation status
  • Cost correlation tooling commitment
  • Enhanced DoD discussion
FEBRUARY 2026 - Evaluation Phase
Week 1-2:
☐ Pilot Test Completion
  • Feature delivery deadline
  • UAT testing and validation
  • Code quality review
  • Comprehensive evaluation report
☐ Market Research Synthesis
  • Evaluate alternative matching engine proposals
  • Compare functionality, cost, integration effort
  • Document feasibility assessment
  • Prepare summary for leadership
Week 3-4:
☐ Pilot Test Debrief
  • Internal evaluation: Success/Partial/Failure?
  • Document lessons learned
  • Assess knowledge transfer viability
  • Decision: Proceed with RFP or focus on relationship improvement?
☐ Hyperscale Decision Preparation
  • Review Moïse performance validation
  • Assess query optimization feasibility (€5-10K alternative)
  • Validate SQL bottleneck claim
  • Prepare recommendation for leadership
MARCH 2026 - Decision Phase
Week 1-2:
☐ Leadership Decision Meeting
  • Present Phase 1 results (pilot, research, negotiation)
  • Recommend Path A/B/C based on data
  • Decision: Vendor switch vs improved relationship vs partial independence
  • Budget allocation for Phase 2
☐ Hyperscale Proposal Decision
  • Approve, reject, or modify based on validation
  • If approved: Plan migration (Q2 2026)
  • If rejected: Implement query optimization alternative
  • Decouple networking security if valuable independently
Week 3-4:
☐ Phase 2 Planning
  • Based on strategic decision, plan next 6-12 months
  • Budget allocation and resource planning
  • Vendor engagement (if transition chosen)
  • Governance improvement roadmap (if relationship improvement chosen)
CISAC (Yann + Moïse + Finance):
• Pilot feature definition
• Vendor selection and contracting
• Contract negotiation leadership
• Monthly cost review participation
• Performance validation (Moïse operational data)
• Strategic decision making (March 2026)
Spanish Point:
• Git history access delivery (December)
• Databricks upgrade roadmap (December)
• Pipeline test runner fix (URGENT)
• Cost correlation tooling discussion
• Contract negotiation participation
• Pilot vendor handover cooperation
Audit Team (Teragone-Factory):
• Pilot test RFP preparation
• Market research coordination
• Contract negotiation support (advisory)
• Performance validation analysis
• Final report delivery (end Nov 2025)
• Phase 1 evaluation synthesis (Feb 2026)
gantt
title Phase 1 Timeline (Dec 2025 - Mar 2026)
dateFormat YYYY-MM-DD
section Pilot Test
Setup & RFP :2025-12-01, 14d
Vendor Selection :2025-12-15, 7d
Development :2025-12-22, 45d
Evaluation :2026-02-05, 14d
section Contract Negotiation
Preparation :2025-12-01, 14d
Kickoff :2025-12-15, 7d
Ongoing Negotiation :2025-12-22, 90d
section Market Research
Vendor Identification :2026-01-06, 14d
Proposals & Demos :2026-01-20, 21d
Synthesis :2026-02-10, 10d
section Performance Validation
Moïse Meetings :2026-01-06, 14d
Data Analysis :2026-01-20, 14d
section Decision
Phase 1 Evaluation :2026-02-17, 7d
Leadership Decision :2026-03-03, 14d
Notes: Let's translate strategy into action. Here's the concrete timeline for the next 4 months.
**December 2025 - Launch Phase:**
Pilot test setup is the priority. Define the feature, identify vendors, send RFPs. Simultaneously, prepare contract renegotiation - document audit findings, prioritize terms, schedule kickoff with Spanish Point.
URGENT: Escalate the pipeline test runner fix. This is blocking since November 4 - unacceptable.
**January 2026 - Execution Phase:**
Pilot vendor begins development. Monitor weekly - track questions, challenges, Spanish Point cooperation.
Start matching engine market research - who else offers music rights matching? Request proposals.
Meet with Moïse - get the operational truth about performance. User complaints, actual metrics, pain points.
First monthly cost review meeting - CISAC + Spanish Point + Finance. Review December spending, correlate with usage manually until tooling exists.
**February 2026 - Evaluation Phase:**
Pilot test completes. Feature delivered, tested, evaluated. Success? Partial? Failure?
Market research synthesized - alternatives exist? Viable? Compatible?
Hyperscale decision preparation - validate SQL bottleneck based on Moïse data and Application Insights analysis.
**March 2026 - Decision Phase:**
Leadership meeting - present Phase 1 results. Recommend Path A/B/C based on evidence, not assumptions.
Hyperscale decision - approve/reject/modify based on validation.
Phase 2 planning - execute the chosen strategy with confidence.
**Responsibilities are clear:**
CISAC leads pilot, negotiation, decisions. Spanish Point delivers fixes and cooperates. Audit team supports with analysis and advisory.
**This is a 4-month sprint to gather the data CISAC needs to make a multi-million-euro strategic decision responsibly.**

## Slide 4
Slide Thank You & Discussion
Thank You
Questions & Discussion
───────────────────────────────────────────────────
Key Contacts:
Audit Team (Teragone-Factory):
Guillaume Jay
Bastien Gallay
Final Report Delivery: End of November 2025
Next Meeting: TBD (Phase 1 results review - February 2026)
───────────────────────────────────────────────────
Today's Key Messages:
✓ Platform is technically solid - not the problem
✓ Governance and control are the challenges
✓ Test knowledge transfer before committing to vendor switch
✓ Use audit findings as leverage for better contract terms
✓ Decide with data (March 2026), not assumptions (today)
───────────────────────────────────────────────────
Open Discussion Topics:
• Which pilot feature makes most sense?
• What vendors should we approach for pilot test?
• Which contract terms are highest priority for CISAC?
• What performance issues have users actually reported?
• Timeline feasibility - can we execute Phase 1 by March 2026?
• Budget allocation - approval for pilot test and market research?
• Other concerns or questions from CISAC leadership?
Notes: Thank you for your time and attention.
We've covered a lot of ground today - from the audit journey to technical findings to strategic recommendations. Let's open the floor for discussion.
**Key messages to remember:**
1. **The platform is technically solid.** Architecture is well-designed, code quality is reasonable, auto-scaling works. These are not the problems.
2. **Governance and control are the challenges.** The May 2024 incident, access delays, cost control gaps, transparency issues - these are organizational and relationship issues, not technical failures.
3. **Test knowledge transfer before committing.** The €10-20K pilot test is the most important investment we're recommending. It de-risks the €300-600K vendor switch decision.
4. **Use audit findings as leverage.** CISAC has negotiating power - use it. Better contract terms are achievable whether you stay or switch.
5. **Decide with data in March 2026, not assumptions today.** Run the pilot. Do the research. Gather the evidence. Then decide.
**Final deliverable:**
We'll deliver the comprehensive final audit report by end of November 2025. It will include all the details, references, and analysis supporting today's presentation.
**Next meeting:**
We propose a Phase 1 results review in February 2026 - evaluate pilot test outcomes, market research findings, and negotiation progress. At that point, we can provide updated recommendations based on actual results.
**Open discussion:**
What questions do you have? What concerns need addressing? What decisions can we help clarify?